# SOFA Trajectory Forecasting — Project Plan

Rolling 6-hour-cadence SOFA forecast over ICU hours 24–48, PhysioNet/CinC Challenge 2012 data. Living document — decision log and experiment tracker are appended to as work proceeds.

Companion to: sofa_calculation.ipynb, sofa_scores.csv, SOFA_modelling_approaches.docx (why the cardiovascular axis is capped and the three candidate approaches), modeling/sofa_forecasting.ipynb, SOFA_forecasting_team_briefing.docx (plain-language version for sharing outside the technical team), and SOFA_forecasting_TRIPOD_AI_checklist.docx (the full 27-item compliance table, split out of this document's former section 7 into its own name). Created 2026-09-10; updated 2026-09-16 (repo moved to github.com/398-21/healthcare-ai-assin; single consolidated notebook; classifier no-skill baseline D18; five-model-family comparison D19-D22; TRIPOD+AI checklist split into its own document).

# 1  Problem definition & problem statement

## 1.1  Motivating problem

Organ dysfunction in critically ill patients evolves hour to hour. SOFA (Sequential Organ Failure Assessment) is the standard organ-failure score but is normally computed once per 24 h, retrospectively. A clinician at the end of ICU day 1 wants to know: over the next day, will this patient's organ-failure burden get worse, and by how much? A model that forecasts the SOFA trajectory 6 h ahead, refreshed every 6 h, converts a retrospective score into an early-warning signal.

## 1.2  Formal problem statement

Population. Adult ICU stays >= 48 h, PhysioNet/CinC Challenge 2012 set A (12,000 stays).

Prediction unit. One (stay, decision-time) pair; decision times T in {24, 30, 36, 42} h after admission (4 per stay).

Inputs. Every measurement and admission descriptor in icu_records/<RecordID>.csv with timestamp < T (expanding window). Nothing from outcomes.csv.

Outputs, per T. (a) six organ sub-scores (each 0–4) for the trailing-24 h window [T−18, T+6), summed to a total SOFA_hat(T+6) in [0, 24]; (b) the delta SOFA_hat(T+6) − SOFA_now; (c) P(SOFA rises >= 2 within 24 h).

Ground truth. The project's rule engine (sofa_calculation.ipynb methodology) applied to the target window. Cardiovascular sub-score is 0/1 — a structural data limitation (no vasopressor drug/dose data), not a modelling choice.

Learning setup. Supervised: regression for sub-scores and delta, binary classification for deterioration. Train on the train split, tune on validation, evaluate once on the held-out test split.

Primary metric. Per-horizon mean absolute error of total SOFA_hat vs the persistence baseline (SOFA_hat = SOFA_now). Secondary: per-axis MAE, deterioration AUROC / AUPRC, calibration.

## 1.3  Scope

In scope. Forecasting the project's rule-based SOFA and its 24–48 h trajectory from icu_records.

Not in scope. Reproducing outcomes.SOFA exactly (already characterised); mortality / length-of-stay prediction; recovering the true cardiovascular sub-score (no drug data); horizons past 48 h (no data); real-time streaming deployment.

## 1.4  Assumptions

The rule-based SOFA is an acceptable proxy for 'true' SOFA past hour 24; the only documented gap is the cardiovascular axis.

icu_records timestamps are accurate elapsed time; the expanding window respects causality.

Each RecordID is an independent ICU stay (no patient linkage exists in this dataset).

Missingness is informative and is kept as signal (indicator features, no blanket imputation).

## 1.5  Known limitations

Cardiovascular capped 0/1 -> total SOFA sits ~1 point below a fully-informed score, on both the feature and the target side. Quantified in SOFA_modelling_approaches.docx.

18 of the 24 target-window hours are already observed at prediction time -> high autocorrelation; the honest, forecastable quantity is the 6 h-ahead delta.

The dataset is a de-identified, down-sampled extract with an early-2010s single-era case mix.

## 1.6  Success criteria

Phase 1. Reproducible split; leak-free feature/target tables; QC counts equal the sofa_calculation.ipynb section-2 audit. MET (2026-09-16).

Project. Total-SOFA forecast beats persistence on the delta at >= 2 of 4 horizons; deterioration AUROC materially > 0.5; per-axis error and the vasopressor-ablation gap quantified and documented. MET AND EXCEEDED (2026-09-17, all 5 families trained for real): 4 of 5 families -- ordinal (D19), histgb (primary), catboost (D21), lightgbm (D22) -- beat persistence at 4 of 4 horizons on both validation and test. The linear/ Ridge baseline (D20) beats persistence only at h24 and is worse at h30/h36/h42 on both splits -- not a bug, but the answer to the question D20 was built to ask: the tree ensembles' non-linearity is earning its keep at the longer horizons, a plain regularized linear model reverts too hard toward the mean delta. Deterioration AUROC 0.78-0.84 for every one of the 4 families with a deterioration classifier (histgb, linear, catboost, lightgbm; ordinal has no classifier variant) vs no-skill 0.5. See section 4 and the notebook's section 13 (Discussion) for the full results and two real bugs (D23, D24) found only by actually running it. The vasopressor-ablation gap (with/without outcomes.SOFA as a feature) is not yet run -- remains an open item.

# 2  Roadmap

As of 2026-09-16 the whole pipeline lives in ONE notebook, modeling/sofa_forecasting.ipynb (TRIPOD+AI item numbers in its section headers); the phase numbers below now refer to its sections rather than separate notebooks. phase1_data.ipynb is retired (D15) -- its content is sections 1-7 of the new notebook.

## Phase 1 — Data preparation & split  [DONE 2026-09-16]

Record-level stratified 70/15/15 split (frozen, seed 42); parse + clean all 12,000 records; build the rolling 6-axis target table at the 4 horizons (absolute, delta, deterioration flag); build the expanding-window feature table; QC report reproducing the notebook audit; leakage checks. Outputs in modeling/outputs/: splits.csv, targets.csv, features.csv.gz, records_clean.joblib, qc_report.md. Result: 48,000 (record x horizon) rows, 407 features; all leakage and QC checks pass; the T=42 target reproduces sofa_scores.csv's SOFA_D2 exactly (r = 1.000); section-7 implausible-value audit matches to the digit. See sofa_forecasting.ipynb sections 1-7 (executed).

## Phase 2 — EDA + baselines  [DONE 2026-09-16]

Target distribution and drift per horizon; feature-target correlation; the persistence baseline (SOFA_hat = SOFA_now) and a last-value-per-axis baseline, with bootstrap-CI MAE / RMSE per horizon (sofa_forecasting.ipynb section 8, executed). Train-split total-SOFA persistence MAE: 0.93 (h24) / 0.69 (h30) / 0.63 (h36) / 0.60 (h42). Also the deterioration classifier's no-skill reference (D18): AUROC 0.5, AUPRC = prevalence (~0.04-0.05 per horizon), Brier ~0.04 by definition. These are the bar Phase 3's models must clear on validation/test.

## Phase 3 — Forecast models  [DONE 2026-09-17 -- all 5 families trained for real]

modeling/models/ is now a package of FIVE model families, compared head-to-head rather than just one tuned family (user-directed 2026-09-16, priority order): (0) models.ordinal -- ordinal regression via Frank & Hall cumulative binary decomposition, predicting the absolute score directly (D19); (1) models.linear -- Ridge/logistic baseline, same delta target as (2), to isolate whether non-linearity helps (D20); (2) models.histgb -- the original primary family: six pooled axis regressors predicting the delta, origin_h as a feature (D12), measured-rows-only (D17), reconstruction = SOFA_now + delta clipped to [0,4] (item 12g), one pooled deterioration classifier (D14); (3) models.catboost_model -- optional dependency, native categorical handling + ordered boosting (D21); (4) models.lightgbm_model -- optional dependency, leaf-wise growth as a second GBDT opinion (D22). Every family uses the same protocol: a small fixed grid, selected on the external validation split (D13, item 12c) -- see section 5 below. CatBoost/LightGBM are NOT installed in the authoring environment; their modules import cleanly regardless (guarded imports) and their training functions raise a clear error only if actually called without the package. sofa_forecasting.ipynb section 10 contains all five training calls; all five ran for real on the training device (catboost 1.2.10, lightgbm 4.7.0 -- D23 fixed the only real bug that surfaced). Result: ordinal (D19) has the lowest total-SOFA MAE at every horizon; histgb, catboost and lightgbm are close together just behind it, with histgb marginally ahead of the other two GBDTs; linear (D20) is the outlier -- it only beats persistence at h24 (see section 1.6). HistGB remains the family worth carrying forward among the three GBDT engines; CatBoost/LightGBM do not clearly improve on it here (open items, section 6).

## Phase 4 — Evaluation  [DONE 2026-09-17]

modeling/evaluate.py + sofa_forecasting.ipynb sections 11-12: per-horizon MAE / RMSE with bootstrap CI for EVERY installed family side by side (evaluate.regression_report, extended to accept an arbitrary {label: column} dict) vs the Phase-2 baselines; per-axis error; deterioration AUROC / AUPRC / Brier + calibration for every family (evaluate.classification_comparison, new) vs the no-skill reference (D18); a subgroup breakdown (hemodynamic-instability status; extend to ICU type / admission-outcomes.SOFA tier); permutation importance (D16, run on the primary family, re-run against whichever family wins). Test split unlocked exactly once, after model selection was final on validation -- test confirms the same ranking seen on validation (section 4), so there is no sign of validation-set overfitting in the family selection. This run also surfaced D24, a fairness bug in how missing axes were scored across families -- see the decision log; every number in section 4 is post-D24-fix.

## Phase 5 — Packaging

predict(record) -> 4-step SOFA forecast function; model-registry entries in this document (section 5); final report.

# 3  Decision log

Each entry: the decision, the options weighed, the choice, and why not the alternatives. Append new entries as D12, D13, … with a date.

## D1  Task = forward forecast, not outcomes.SOFA reconstruction

Chosen: Forecast the rolling SOFA forward over hours 24–48.

Rejected: Pure outcomes.SOFA regression — already characterised (r 0.93, −0.86 bias), adds no trajectory signal. Mortality / LOS model — a different project.

## D2  Four horizons x trailing-24 h target window

Chosen: Predict at T in {24,30,36,42} h; target = a standard 24 h-length SOFA window ending at T+6, i.e. [6,30), [12,36), [18,42), [24,48) h.

Rejected: 6 h-window SOFA — non-standard, noisy, labs often absent within 6 h. Single horizon — trivial once the 4-horizon pipeline exists.

## D3  Expanding input window

Chosen: At decision time T the model sees icu_records[0, T) — more data at later horizons.

Rejected: Fixed [0,24) h features for every horizon — unrealistic; you do have the newer data at h36. Cost accepted: 4 rows per record and strict leakage discipline (feature window [0,T) never touches [T, T+6)).

## D4  Six-axis decomposition (Approach 2 from SOFA_modelling_approaches.docx)

Chosen: Model each organ sub-score (0–4) separately, then sum.

Rejected: Monolithic SOFA regressor — opaque, cannot isolate the cardiovascular weakness. Raw-physiology-to-outcome (Approach 3) — a different deliverable.

## D5  Cardiovascular capped 0/1 on both feature and target side, past hour 24

Chosen: Accept the rule's 0/1 cardiovascular score everywhere; carry a 'hemodynamic instability' flag (min MAP < 65 in the window) alongside.

Rejected: Imputing pressor points from proxies for the target — would fabricate ground truth. There is no reference SOFA after hour 24 and no drug data anywhere.

## D6  outcomes.csv is never a model input

Chosen: Features derive only from icu_records[0, T) (this includes our own rule SOFA on [0,24) h and on [T−24, T) h — those are computed from our data). outcomes.csv is used at evaluation only, plus one Phase-4 with/without ablation.

Rejected: Feeding raw outcomes.SOFA as a feature — it is the outcome, not the data, and is unavailable at inference. A model trained to reconstruct outcomes.SOFA and used as an 'anchor' feature — over-built and still blurs the outcome/data boundary.

## D7  Target reported as absolute score AND delta vs SOFA_now

Chosen: Model and report SOFA_hat(T+6) and SOFA_hat(T+6) − SOFA_now.

Rejected: Absolute score only — ~80 % of it is just current severity; the delta isolates the forecastable part and is the clinically useful signal.

## D8  Model family = sklearn HistGradientBoosting

Chosen: HistGradientBoostingRegressor / Classifier — native NaN handling for this sparse data, no extra install, competitive accuracy.

Rejected: LightGBM / XGBoost — not installed in this environment; marginal gains. Deep sequence models — premature; revisit only if the tabular ceiling is clearly limiting.

## D9  Split = record-level, stratified, 70/15/15, seed 42, test frozen

Chosen: All four horizon-rows of a record share its split. Stratify on SOFA-severity band x in-hospital death; SOFA == -1 records form their own band. Test untouched until Phase 4.

Rejected: Row-level split — leaks a record's trajectory across train/test. Patient-level grouping — no patient IDs exist. Time-based split — no admission dates.

## D10  Cohort

Chosen: Forecast tables use all 12,000 records — targets are self-computed. Rows whose target window has no measurement keep NaN scores and are excluded at evaluation.

Rejected: Restricting to the 11,597 SOFA-labelled records — unnecessary, since the forecast target does not come from outcomes.csv.

## D11  Single source of truth for scoring

Chosen: modeling/data_prep/scoring.py is the canonical rule engine; sofa_calculation.ipynb imports it on its next rebuild. Rules unchanged from the methodology doc.

Rejected: Duplicating the scoring logic in two places — guarantees drift.

## D12  Six pooled axis models, not 24 separate ones  (2026-09-16)

Chosen: One HistGradientBoostingRegressor per organ axis (6 total), trained on all four horizons pooled together with origin_h as an ordinary feature — 33,600 train rows per model instead of 8,400.

Rejected: 24 separate axis x horizon models — 4x less data per model, 4x the artefacts to store and tune; origin_h already lets one pooled model learn horizon-dependent effects via splits.

## D13  Hyperparameter tuning = small fixed grid, external-validation selection  (2026-09-16)

Chosen: learning_rate in {0.05, 0.1} x max_leaf_nodes in {31, 63} (4 combinations), max_iter=300, l2_regularization=0.0, random_state=42, fixed across all 6 regressors + the classifier. Each point is fit on train and scored on the untouched validation split; the winner and every grid point's score are logged (sofa_forecasting.ipynb section 9).

Rejected: HistGB's internal early_stopping / validation_fraction — carves its own validation rows out of train silently, which is harder to report transparently under TRIPOD+AI item 12c. A larger/automated search (e.g. HalvingGridSearchCV, Optuna) — deferred: not installed, and a 4-point grid is honestly reported as modest rather than implying more rigour than was actually applied.

## D14  Deterioration classifier: pooled, class-weighted  (2026-09-16)

Chosen: One pooled HistGradientBoostingClassifier (origin_h as a feature), class_weight='balanced' for the ~4% positive rate; selected by validation AUPRC (not AUROC, which is optimistic under this much imbalance) — item 13.

Rejected: Resampling (SMOTE / undersampling) — an extra dependency and an extra source of leakage risk (must resample train only) for a benefit class_weight already gives natively.

## D15  Single consolidated notebook supersedes phase1_data.ipynb  (2026-09-16)

Chosen: modeling/sofa_forecasting.ipynb is self-sufficient end to end (re-parses icu_records/ if the cache is absent) and covers preprocessing through evaluation in one document with TRIPOD+AI-tagged section headers. phase1_data.ipynb is deleted; git history keeps it recoverable.

Rejected: Keeping both notebooks — two partially-overlapping sources of truth for the same preprocessing code invites drift.

## D16  Permutation importance scoped for tractability  (2026-09-16)

Chosen: n_repeats=3 on a fixed random 2,000-row subsample of validation, per model (7 models) — HistGB has no built-in feature_importances_, and the full ~33,600-row pooled validation set x 407 features x repeats would be materially slower for a portfolio-scale project.

Rejected: Full-validation-set permutation importance — more precise but not worth the wall-clock cost here; the subsample size and repeat count are logged, not hidden.

## D17  Axis-model training rows: measured-only, never lenient zero-fill  (2026-09-16)

Chosen: Each axis regressor trains only on (record, horizon) rows where that specific axis had a real measurement in the target window (dropna on {axis}_delta). Sample size therefore differs by axis (e.g. ~33,000 for cardio/neuro/renal vs ~13,500 for liver, which is measured far less often) and is reported per axis (item 21).

Rejected: Training on the lenient zero-filled sofa_total convention (used for the aggregate score, D10) — would teach the model that 'never measured' means 'score 0', fabricating signal that isn't there.

## D18  No-skill baseline added for the deterioration classifier  (2026-09-16)

Chosen: evaluate.no_skill_reference(): AUROC of a non-informative classifier is always 0.5, but AUPRC of one equals the outcome's prevalence (~4%), not 0.5 (Saito & Rehmsmeier, PLOS ONE 2015) — with this much imbalance a model can post an AUPRC around 0.15-0.20 and look skilled while barely beating a coin flip. Computed in notebook section 8 (train split, per horizon) and reported alongside the real classifier in section 11.

Rejected: Leaving the deterioration classifier without any documented comparator, unlike the regression side (persistence baseline) — an asymmetry a careful review would catch; fixed proactively rather than left for a reviewer to flag.

## D19  Ordinal-regression framing added as a second axis-modelling approach  (2026-09-16)

Chosen: modeling/models/ordinal.py: each axis score (0-4) is treated as an ORDINAL outcome via Frank & Hall's (2001) cumulative binary decomposition -- 4 HistGradientBoostingClassifiers per axis, one per threshold k in {0,1,2,3}, each predicting P(score > k). Reconstruction uses E[score] = P(>0)+P(>1)+P(>2)+P(>3), the tail-sum identity for a bounded non-negative integer variable -- lands in [0,4] automatically, no clipping. Predicts the ABSOLUTE target score directly (no delta trick: SOFA_now is just an input feature here). Compared head-to-head against histgb.py's delta-regression in the Results section, not a replacement. No monotonicity constraint across the four thresholds is enforced -- a known, logged simplification of the method.

Rejected: mord / statsmodels OrderedModel (classical proportional-odds implementations) -- would add an external dependency for a linear-only ordinal model, when the binary-decomposition approach lets us reuse the same HistGB engine (and later CatBoost/LightGBM) as a base learner, keeping the model-family comparison apples-to-apples.

## D20  Ridge / logistic linear baseline added  (2026-09-16)

Chosen: modeling/models/linear.py: median-impute + standardize + Ridge (regressor) or class-weighted LogisticRegression (classifier), same delta target and feature set as histgb.py, to isolate whether the tree ensembles' non-linearity is earning its keep over a plain regularized linear model. Small grid (alpha / C in {0.1, 1.0, 10.0}), same external-validation-selection protocol as every other family.

Rejected: Skipping a linear baseline entirely -- would leave 'is the complexity worth it' as an assumption rather than a measured result; TRIPOD+AI's own title names regression models alongside ML models as the expected comparison.

## D21  CatBoost added as a GBDT alternative  (2026-09-16)

Chosen: modeling/models/catboost_model.py: native categorical handling for ICUType/Gender/origin_h, and ordered boosting (CatBoost's overfitting-reduction mechanism, most relevant on our smaller axes, e.g. liver at ~13,500 training rows). NOT installed in the authoring environment -- import is guarded (`CATBOOST_AVAILABLE` flag) so `import modeling.models` still succeeds here; every train_*/fit_* function raises a clear ImportError only if actually called without the package. Same delta target, same external-validation grid protocol as histgb.py, for a fair comparison.

Rejected: Installing catboost in the authoring environment just to satisfy an import -- unnecessary and this environment is not where training happens; the guard pattern gets the same outcome (importable module, correct code) without the dependency.

## D22  LightGBM added as a second GBDT opinion  (2026-09-16)

Chosen: modeling/models/lightgbm_model.py: leaf-wise (best-first) tree growth, a different bias than HistGB's/CatBoost's more level-wise growth, and native missing-value routing like HistGB (no imputation, unlike linear.py). Same guarded-import pattern as D21 (NOT installed here), same delta target and grid protocol as histgb.py.

Rejected: Treating HistGB as the only GBDT worth trying -- leaf-wise vs level-wise growth is a real, not merely cosmetic, modelling choice on data this size, and worth measuring rather than assuming away.

## D23  CatBoost categorical-feature dtype bug found + fixed on first real run  (2026-09-17)

Chosen: modeling/models/catboost_model.py: CatBoost's cat_features columns must be int or str, never raw float/NaN -- passing origin_h=24.0 straight from pandas raised 'CatBoostError: real number values and NaN values should be converted to string', caught the moment the training device (which has catboost installed) actually ran notebook section 10.3. Fixed with `_prepare_categoricals()`: fillna(-1).astype(int).astype(str) on d_icutype/d_gender/origin_h, applied identically at fit time (train + val) and at prediction time, so the model never sees a representation it wasn't trained on. This is exactly what D21's caveat anticipated -- the module was 'import-checked, never executed' in the authoring environment because catboost wasn't installed there; the categorical-dtype requirement only surfaces once you actually call .fit() with real data, which nothing short of running it on real hardware would have caught.

Rejected: Casting the categorical columns to pandas 'category' dtype instead of plain strings -- CatBoost's sklearn API documentation specifically calls out int/str, and 'category' dtype has its own edge cases (e.g. unseen categories at predict time) not worth introducing for 3 small-cardinality columns.

## D24  Missing-axis fairness bug found on first full Results run -- fixed in all 5 families  (2026-09-17)

Chosen: Discovered via a two-step investigation: (1) ordinal's per-threshold calibration was excellent (predicted P(score>k) matched observed almost exactly, every axis/threshold) yet its total-SOFA MAE was catastrophically bad (~1.3-1.45, worse than persistence) -- a contradiction; (2) only 21.8% of rows have all six sofa_now_<axis> columns present at once (resp missing 49%, liver missing 60%), matching exactly the n≈360/1795 that evaluate.regression_report's internal dropna() was silently restricting the delta families to, vs n=1795 (the full population) for persistence and ordinal. The delta families were being scored on an artificially easy complete-case subset while ordinal/ persistence were scored on the full, harder population -- not a valid comparison. Fix: every family's predict_axis_scores_*() now applies the same gate -- has_now = ~isnan(sofa_now_<axis>); pred = has_now ? real_prediction : 0.0 -- matching the project's lenient missing-axis-scores-0 convention (D10) instead of letting delta families go silently NaN (excluded from scoring) or letting ordinal's classifiers guess a nonzero score with no real anchor. The per-axis persistence baseline itself was fixed the same way (sofa_now_<axis>.fillna(0.0)) so every series in every comparison table is now evaluated on the identical n. Re-running only the results/interpretation steps (no retraining needed) produced the current, much more sensible result set in section 4.

Rejected: Leaving the complete-case subset as-is and just footnoting the n mismatch -- would still make the delta-family numbers look better than they are relative to ordinal/persistence, for reasons having nothing to do with model quality. Restricting ALL families to the complete-case subset instead of the lenient zero-fill -- throws away ~78% of the evaluation population and stops answering the question the project's own sofa_total convention (D10) actually asks.

# 4  Experiment tracker

One row per model run. Fill after each Phase-2/3 experiment. 'vs base' = MAE improvement over the Phase-2 persistence baseline for that horizon.

| Exp ID | Date | Phase | Model / features | Target | Horizon | Split | MAE (RMSE) | vs base |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| BASE-1 | 2026-09-16 | 2 | persistence: SOFA_hat = SOFA_now | total SOFA | all 4 | train | 0.93/0.69/0.63/0.60 | — |
| BASE-2 | 2026-09-16 | 2 | last-value-per-axis carried forward | 6 sub-scores | all 4 | train | see qc_report.md | — |
| BASE-3 | 2026-09-16 | 2 | no-skill reference (D18): AUROC .5 / AUPRC=prevalence | deteriorate_24h | all 4 | train | AUPRC .038-.045 | — |
| M-0 | 2026-09-17 | 3 | ordinal (D19): Frank & Hall decomposition, HistGB base | total SOFA | 24/30/36/42 | test | 0.629/0.601/0.597/0.536 | +0.328/+0.105/+0.048/+0.058 (best of 5) |
| M-1 | 2026-09-17 | 3 | linear (D20): Ridge, delta target | total SOFA | 24/30/36/42 | test | 0.798/0.728/0.722/0.681 | +0.159/-0.022/-0.077/-0.087 (worse at 3/4 horizons) |
| M-2 | 2026-09-17 | 3 | histgb (primary, D12-14/17): pooled delta regression | total SOFA | 24/30/36/42 | test | 0.651/0.619/0.610/0.553 | +0.306/+0.087/+0.035/+0.041 (best of 3 GBDTs) |
| M-3 | 2026-09-17 | 3 | catboost (D21): ordered boosting, delta target | total SOFA | 24/30/36/42 | test | 0.677/0.635/0.619/0.561 | +0.280/+0.071/+0.026/+0.033 |
| M-4 | 2026-09-17 | 3 | lightgbm (D22): leaf-wise GBDT, delta target | total SOFA | 24/30/36/42 | test | 0.649/0.626/0.615/0.560 | +0.308/+0.080/+0.030/+0.034 |
| M-5 | 2026-09-17 | 4 | deterioration (>=2 SOFA rise, D14): histgb/catboost/lightgbm/linear classifiers vs no-skill (D18, AUROC .5/AUPRC .045) | deteriorate_24h | pooled | test | AUROC .838/.837/.820/.780; AUPRC .308/.280/.297/.175 | all >> no-skill; ordinal has no classifier variant |

# 5  Configuration reference

Mirrors modeling/config.py — the single source for paths and task geometry.

SEED = 42

HORIZONS_H = (24, 30, 36, 42)   — decision times T

FORECAST_AHEAD_H = 6   — predict as of T + 6

TARGET_WINDOW_H = 24   — target scored over [T−18, T+6) h

NOW_WINDOW_H = 24   — SOFA_now scored over [T−24, T) h

DETERIORATE_DELTA = 2   — deterioration = SOFA rises >= 2 within 24 h

SPLIT_RATIOS = (0.70, 0.15, 0.15)

PAIR_WINDOW_MIN = 120 ; URINE_MIN_SPAN_MIN = 1200   — rule-scoring constants (unchanged from the doc)

modeling/models/histgb.py REGRESSOR_GRID (D13): learning_rate in {0.05,0.1} x max_leaf_nodes in {31,63}, max_iter=300, l2_regularization=0.0, random_state=42 — 4 configurations per axis; CLASSIFIER_GRID (D14): as above + class_weight='balanced'

modeling/models/ordinal.py GRID (D19): same shape as histgb's REGRESSOR_GRID, one set of 4 configs per threshold (4 thresholds x 6 axes = 24 threshold-models)

modeling/models/linear.py RIDGE_GRID / LOGISTIC_GRID (D20): alpha / C in {0.1, 1.0, 10.0}; logistic adds class_weight='balanced'

modeling/models/catboost_model.py REGRESSOR_GRID (D21, optional dep.): learning_rate in {0.05,0.1} x depth in {4,6}, iterations=300

modeling/models/lightgbm_model.py REGRESSOR_GRID (D22, optional dep.): learning_rate in {0.05,0.1} x num_leaves in {31,63}, n_estimators=300

Model registry (populated once Phase 3 is run on the training device): modeling/outputs/models/<family>/axis_<name>.joblib, deteriorate_24h.joblib (one subfolder per trained family), plus model_spec.json

# 6  Open items — to decide as work proceeds

RESOLVED (2026-09-17): 'which of the five families to carry forward' — ordinal (D19) wins on total-SOFA MAE at every horizon; histgb is the best of the three GBDT engines, with CatBoost/LightGBM not clearly improving on it; the linear baseline (D20) does NOT close the gap — it is the only family that fails to beat persistence past h24. Recommendation: carry ordinal forward as primary, keep histgb as the interpretable/fast fallback, drop CatBoost/LightGBM unless a future need (e.g. GPU training at larger scale) reappears.

RESOLVED (2026-09-17): catboost 1.2.10 / lightgbm 4.7.0 installed and run for real on the training device. catboost's categorical-dtype bug (D23) was the only real issue caught; lightgbm required no fix. A second, more serious bug (D24) was found in the shared evaluation/reconstruction code, not in either optional-dependency module.

NEW open item (2026-09-17, from D24): ordinal's advantage is measured only under the fairness gate (predict 0 when sofa_now_<axis> is missing); an ablation WITHOUT the gate would show whether ordinal's classifiers can usefully guess from indirect evidence when an axis has no direct anchor -- a capability the current headline comparison deliberately does not exercise.

Split ratio (currently 70/15/15) and stratification key — revisit if any family is starved of a rare stratum; not observed as an issue in the 2026-09-17 run.

Feature list is deliberately broad (~400 columns); prune by permutation importance (D16) — run in notebook section 13 for the primary family; a full cross-family importance comparison remains future work.

deteriorate_24h threshold: >= 2 total, or a per-axis 'any organ worsens by >= 1' rule — revisit with clinical input; the current threshold's classifiers (AUROC 0.78-0.84) already show clear skill over no-skill (D18), so this is a refinement, not a blocker.

Ordinal framing (D19) has no monotonicity constraint across its four thresholds — worth revisiting given D24 showed ordinal wins the headline comparison; no evidence yet that the lack of a constraint hurts it in practice, but it hasn't been specifically checked.

The with/without-outcomes.SOFA feature ablation (Phase 4, D6) — not yet run; the vasopressor-ablation gap this exists to quantify remains the project's largest genuinely open item.

Formal fairness-metric stratification by age/sex (TRIPOD+AI item 14) — deferred; this cohort's size may not support stable subgroup estimates once split by both age band and sex.

Calibration: the deterioration classifier's calibration table (section 4) shows the top decile OVER-predicting observed risk (test: mean_pred 0.696 vs observed_rate 0.220 in the top bin) — the model's probabilities are not directly usable as calibrated risk estimates even though ranking (AUROC/AUPRC) is strong; a recalibration step (Platt/isotonic) is worth adding before any real-world use of the predicted probabilities themselves.

# 7  TRIPOD+AI checklist

Moved to its own document — SOFA_forecasting_TRIPOD_AI_checklist.docx — so the full 27-item compliance table has a clear, dedicated, shareable name instead of being buried as a section here (2026-09-16). That document also lists the five model families in scope (D19-D22 + the primary, D12-D14/D17) and a status summary (Reported / Partial / N/A / pending execution). This section is kept only as a pointer so nobody goes looking for it here by habit.